WEBSITE DEVELOPMENT

QUOTATION & MILESTONE SCHEDULE

Prepared by: Kohasa Group Digital Team

Prepared for: [Client Name] — INSERT CLIENT NAME

Project: KohasaConstruction.com — New Website Design & Development

Quotation Ref: KCCL-WEB-2026-001

Date: 21 May 2026

Validity: 30 days from date of issue

Estimated Duration: 4 weeks (28 calendar days) from signed acceptance

1. PROJECT SCOPE & DELIVERABLES

This quotation covers the full design and development of the Kohasa Construction Company Limited website (KohasaConstruction.com) — a new standalone site for the Construction Division of the Kohasa Group, linked to the existing KohasaEng site.

1.1  SHARED GROUP LANDING PAGE

- New shared Kohasa Group portal page — displayed on both kohasaeng.com and kohasaconstruction.com

- Two division cards linking to KohasaEng homepage and KohasaConstruction homepage respectively

- Key group statistics, contact strip, and footer

1.2  KOHASACONSTRUCTION HOMEPAGE

- Full homepage with sticky navigation, hero section with real KPI stats (20+ yrs, 14,092 m2, 0 LTI, NGN5B+)

- Three core service lines: Construction & Fabrication, Industrial Maintenance, Specialist Field Services

- Photo gallery grid sourced from SharePoint media library

- Fabrication yard specifications panel (14,092 m2, 1,500t jetty, river access)

- 9-capability technical grid (piping, platforms, tanks, pipelines, NDT, civil, structural, metering, LPG/CPF)

- Six featured project reference cards (Shell SNEPCO, WAGL/Escravos, Green Energy/Lekoil, Heirs Energies, Newcross/Awoba, FPSO Bonga)

- HSE record panel: 0 LTI, 0 Fatalities, 0 Environmental Incidents (2021-2025)

- Client portfolio: 15 named clients including Shell, TotalEnergies, ExxonMobil, Heirs Energies, Seplat

- 8 credentials & certifications: ISO 9001/14001/45001, COREN, ACEN, NIPEX, IMS, ASNT

- Group advantage section + CTA + footer with 3 office addresses (PH HQ, Fabrication Yard, Lagos)

1.3  KOHASAENG HOMEPAGE UPDATE

- Group top bar added to existing KohasaEng site with link back to Construction

- Navigation updated with KohasaConstruction cross-link button

- Sister-site bar in footer linking to KohasaConstruction and Group Overview

1.4  TECHNICAL & INTEGRATION

- Full mobile-responsive design (tested across desktop, tablet, and mobile breakpoints)

- WordPress-compatible HTML/CSS files ready for upload

- Image integration from Kohasa SharePoint media library

- URL and internal link configuration between both sites

- One round of revisions included post-delivery

- Handover documentation and link update guide

2. COST BREAKDOWN

All fees are quoted in Nigerian Naira (NGN). VAT applicable at the prevailing rate (currently 7.5%) where required by law.

| # | DELIVERABLE | DESCRIPTION | AMOUNT (NGN) |
| --- | --- | --- | --- |
| 1 | Shared Group Landing Page | Design & build of the Kohasa Group portal — the shared front door for both kohasaeng.com and kohasaconstruction.com. Includes hero, two division cards, stats bar, and footer. | 480,000 |
| 2 | KohasaConstruction Homepage | Full homepage design & development: navigation, hero, service lines (3), fabrication yard panel, photo gallery (5 images), 9-capability grid, 6 project reference cards, HSE panel, client portfolio, 8 credentials cards, group advantage section, CTA, footer. | 1,650,000 |
| 3 | KohasaEng Homepage Update | Integration of group top bar, cross-link nav button, and sister-site footer bar into the existing KohasaEng site. Ensures seamless navigation between both divisions. | 220,000 |
| 4 | Image Integration | Sourcing, optimising, and placing images from the Kohasa SharePoint media library across the Construction homepage photo grid and hero sections. | 150,000 |
| 5 | Mobile Responsive Development | Full responsive testing and optimisation across desktop, tablet (768px), and mobile (375px) breakpoints for all three pages. | 180,000 |
| 6 | WordPress Upload & Configuration | Uploading all HTML/CSS files to WordPress, configuring page URLs, testing all internal cross-links between kohasaeng.com and kohasaconstruction.com. | 240,000 |
| 7 | Revision Round (1x) | One complete round of client-requested revisions following initial delivery, including content, layout, and colour adjustments. | Included |
| 8 | Handover & Documentation | URL update guide, link configuration notes, and post-handover support instructions (PDF). | Included |
| SUBTOTAL |  |  | 2,920,000 |
| VAT (7.5%) |  |  | 219,000 |
| TOTAL | TOTAL PROJECT FEE | All items above ¦ VAT inclusive | NGN 3,139,000 |

Note: Domain registration/hosting costs for kohasaconstruction.com are not included in this quotation. Client is responsible for procuring and configuring the domain and hosting environment.

Exchange rate note: USD equivalent is approximately USD 1,750 at a rate of NGN 1,794/$1 (May 2026). Final invoicing in NGN.

3. PAYMENT SCHEDULE

| PAYMENT | TRIGGER | AMOUNT (NGN) | TIMING |
| --- | --- | --- | --- |
| 1st Instalment — Mobilisation Fee | Contract signed and accepted | 1,255,600 | Day 0 (before work begins) |
| 2nd Instalment — Delivery Milestone | Delivery of all pages for client review | 1,255,600 | Day 21 (3 weeks) |
| 3rd Instalment — Final Sign-Off | Revisions complete, files uploaded to WordPress, handover done | 627,800 | Day 28 (project close) |
| TOTAL |  | NGN 3,139,000 | VAT inclusive |

Payment terms: Each instalment payable within 5 business days of the stated trigger. Bank details will be provided on the formal invoice.

4. PROJECT MILESTONES & SCHEDULE

Timeline commences from the date of receipt of signed acceptance and 1st instalment payment.

| # | MILESTONE | DELIVERABLE / TRIGGER | TIMING | % OF TOTAL |
| --- | --- | --- | --- | --- |
| M1 | Contract Signed & Mobilisation | Signed quotation acceptance + 1st instalment received | Day 0 | — |
| M2 | Kickoff & Content Lock | Client confirms: domain URL, all image assets shared, any content corrections agreed | Day 1–3 | — |
| M3 | Shared Group Landing Page — Delivered | Group portal page (HTML file) delivered for client review | Day 7 | ~16% |
| M4 | KohasaConstruction Homepage — Delivered | Full construction homepage (HTML file) delivered for client review | Day 14 | ~57% |
| M5 | KohasaEng Update — Delivered | Updated KohasaEng homepage with cross-links delivered | Day 16 | ~7% |
| M6 | Client Review Period | Client reviews all 3 pages and provides consolidated feedback (1 round) | Day 17–20 | — |
| M7 | 2nd Instalment Due | All pages delivered for review — 2nd payment triggered | Day 21 | 40% |
| M8 | Revisions Complete | All client-requested revisions implemented and re-submitted | Day 24 | — |
| M9 | WordPress Upload & Go-Live | All files uploaded to WordPress, links configured and tested on live domains | Day 26–27 | — |
| M10 | Final Handover & Sign-Off | Handover document issued. Final instalment due upon client sign-off. | Day 28 | 20% |

Timeline assumptions: The above schedule assumes client feedback is provided within 3 business days of each delivery. Delays in client feedback, content supply, or payment of milestones will extend the project timeline proportionally.

Revisions: One (1) consolidated round of revisions is included. Additional revision rounds beyond this scope will be quoted separately at NGN 95,000 per round.

5. TERMS & CONDITIONS

- This quotation is valid for 30 days from the date of issue.

- Work commences upon receipt of the signed acceptance and the first instalment payment.

- All deliverables remain the intellectual property of Kohasa Construction Company Limited upon full and final payment.

- Client is responsible for providing: domain and hosting access, SharePoint image assets, and any content corrections within the agreed timeline.

- Additional pages (e.g. Services subpages, Projects gallery, Careers page) beyond this scope can be quoted separately.

- Cancellation after kickoff: the first instalment is non-refundable. Cancellation after M4 (page delivery): 70% of total fee is payable.

6. ACCEPTANCE

To accept this quotation, please sign below and return with proof of the first instalment payment.

| Client Signature Full Name & Title Date |  | For Kohasa Group Name & Title Date |
| --- | --- | --- |

Kohasa Construction Company Limited

Plot 474, Trans-Amadi Industrial Layout, Port Harcourt, Rivers State, Nigeria

Tel: +234 (0)1 255 0161 / 0162   |   Email: info@kohasaeng.com   |   Web: kohasaeng.com